## Teams
TeamID | TeamName | Product / Service | SprintLengthDays | BaseVelocityPts | TeamSize | Timezone | DeliveryManager
TEAM-01 | Payments Squad | Checkout & Payment Platform | 14 | 30 | 6 | IST | <PERSON>
TEAM-02 | Identity Guild | Customer Identity & Access | 14 | 28 | 5 | IST | <PERSON>
TEAM-03 | Platform Team | Cloud Platform & APIs | 14 | 32 | 7 | IST | <PERSON>

## TeamMembers
MemberID | TeamID | Name | Role | Seniority | AllocationPct | CapacityHrsPerSprint | Location | StartDate
USR-001 | TEAM-01 | <PERSON> <<EMAIL_ADDRESS>> | Product Owner | Lead | 100 | 70 | Pune | 2025-01-09
USR-002 | TEAM-01 | <PERSON> <<EMAIL_ADDRESS>> | Developer | Senior | 100 | 70 | Mumbai | 2025-02-10
USR-003 | TEAM-02 | <PERSON> (<PHONE_NUMBER>) | Developer | Senior | 100 | 70 | Bengaluru | 2025-03-12
USR-004 | TEAM-02 | <PERSON> | QA Engineer | Mid | 100 | 70 | Hyderabad | 2025-04-15
<PERSON> | TEAM-03 | <PERSON> | DevOps Engineer | Senior | 100 | 70 | Pune | 2025-05-20

## Sprints
SprintID | TeamID | SprintName | StartDate | EndDate | WorkingDays | PlannedCapacityPts | CommittedPts | Status
SPR-01 | TEAM-01 | Sprint 1 | 2026-07-07 | 2026-07-20 | 10 | 30 | 28 | Completed
SPR-02 | TEAM-01 | Sprint 2 | 2026-07-21 | 2026-08-03 | 10 | 30 | 32 | Completed
SPR-03 | TEAM-02 | Sprint 1 | 2026-07-07 | 2026-07-20 | 10 | 28 | 26 | Completed
SPR-04 | TEAM-02 | Sprint 2 | 2026-07-21 | 2026-08-03 | 10 | 28 | 30 | Completed
SPR-05 | TEAM-03 | Sprint 1 | 2026-07-07 | 2026-07-20 | 10 | 32 | 30 | Completed
SPR-06 | TEAM-03 | Sprint 2 | 2026-07-21 | 2026-08-03 | 10 | 32 | 34 | Completed
SPR-07 | TEAM-01 | Sprint 3 | 2026-08-04 | 2026-08-17 | 10 | 30 | 30 | Planned
SPR-08 | TEAM-02 | Sprint 3 | 2026-08-04 | 2026-08-17 | 10 | 28 | 28 | Planned
SPR-09 | TEAM-03 | Sprint 3 | 2026-08-04 | 2026-08-17 | 10 | 32 | 32 | Planned

## Holidays
HolidayID | Location | Date | HolidayName | ImpactedTeamID
HOL-01 | Maharashtra | 2026-08-15 | Independence Day | TEAM-01
HOL-02 | Karnataka | 2026-08-15 | Independence Day | TEAM-02
HOL-03 | Maharashtra | 2026-08-15 | Independence Day | TEAM-03

## SAD_Sections
SectionID | SADTitle | SectionNumber | SectionTitle | ArchitectureLayer | Summary
SAD-01 | Payment Platform S-AD v1.0 | 2.1 | Payment Services | Backend | Payment authorization, transaction orchestration, and gateway integration.
SAD-02 | Identity Platform S-AD v1.0 | 2.2 | Identity & Access Management | Identity | OAuth2/OIDC authentication, RBAC, token and session management.
SAD-03 | Cloud Platform S-AD v1.0 | 2.3 | Cloud Infrastructure | Infrastructure | AWS networking, APIs, observability, and platform services.

## Backlog
TicketID | Type | Title | ParentID | SADSectionID | Layer | StoryPoints | Priority | Status | SprintID | AssigneeID | HasAcceptanceCriteria | HasDoD | Labels | CreatedDate
EPIC-01 | Epic | Payment Checkout Modernization |  | SAD-01 | Backend |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-01
EPIC-02 | Epic | Identity Modernization |  | SAD-02 | Identity |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-02
EPIC-03 | Epic | Cloud API Platform |  | SAD-03 | Infrastructure |  | High | In Progress |  |  | Y | Y | epic | 2026-06-03
PAY-101 | Story | Add OTP validation to checkout for <PERSON> <<EMAIL_ADDRESS>> | EPIC-01 | SAD-01 | Backend | 5.0 | High | Done | SPR-01 | USR-002 | Y | Y | payment,otp | 2026-06-05
PAY-102 | Story | Add payment retry handling | EPIC-01 | SAD-01 | Backend | 8.0 | High | Done | SPR-02 | USR-002 | Y | Y | payment,retry | 2026-06-06
PAY-103 | Story | Protect checkout API with customer email <EMAIL_ADDRESS> | EPIC-01 | SAD-01 | Backend | 5.0 | Medium | In Progress | SPR-07 | USR-001 | Y | Y | payment,security | 2026-06-07
ID-101 | Story | Implement OAuth2 login | EPIC-02 | SAD-02 | Identity | 8.0 | High | Done | SPR-03 | USR-003 | Y | Y | oauth,identity | 2026-06-08
ID-102 | Story | Add session timeout policy | EPIC-02 | SAD-02 | Identity | 5.0 | Medium | Done | SPR-04 | USR-004 | Y | Y | session,identity | 2026-06-09
ID-103 | Story | Add RBAC audit events | EPIC-02 | SAD-02 | Identity | 5.0 | Medium | In Progress | SPR-08 | USR-004 | Y | Y | rbac,audit | 2026-06-10
PLAT-101 | Story | Create private API endpoint | EPIC-03 | SAD-03 | Infrastructure | 8.0 | High | Done | SPR-05 | <PERSON> | Y | Y | api,networking | 2026-06-11
PLAT-102 | Story | Add API monitoring dashboard | EPIC-03 | SAD-03 | Infrastructure | 5.0 | Medium | Done | SPR-06 | <PERSON> | Y | Y | monitoring | 2026-06-12
PLAT-103 | Story | Rotate demo API key api_key=<SECRET_VALUE> | EPIC-03 | SAD-03 | Infrastructure | 3.0 | High | In Progress | SPR-09 | <PERSON> | Y | Y | security,secrets | 2026-06-13

## Dependencies
DependencyID | FromTicketID | ToTicketID (depends on) | DependencyType | Notes
<PERSON> | PAY-103 | PAY-101 | Blocks | Checkout security story depends on OTP validation.
DEP-002 | PAY-102 | PLAT-101 | Blocks | Payment retry handling depends on private API endpoint.
DEP-003 | ID-103 | ID-101 | Blocks | RBAC audit work depends on OAuth2 foundation.
DEP-004 | PAY-103 | ID-101 | Blocks | Checkout security integration depends on identity authentication.

## ChangeRequests
CRID | ReceivedDate | Source | RawText | SuggestedType | PotentialDuplicateOf | TargetSprintID | Status
CR-001 | 2026-08-04 | Workshop note | <PERSON> <<EMAIL_ADDRESS>> requested SMS notification for checkout status. | Story |  | SPR-07 | New
CR-002 | 2026-08-05 | Product review | Please contact <PHONE_NUMBER> if payment authorization fails. | Story |  | SPR-07 | New
CR-003 | 2026-08-06 | Security review | Use password=<SECRET_PASSWORD> only for local testing; do not store it. | Task |  | SPR-09 | New

## Intake_Samples
IntakeID | IntakeMode | Title | RawContent | SourceStakeholder
INT-01 | One-line ask | <PERSON> | Create a story so <PERSON> can use OTP validation during checkout. Email: <EMAIL_ADDRESS> | Product Management
INT-02 | One-line ask | Payment incident | If the payment service fails, call <PHONE_NUMBER> and notify the support contact. | Support
INT-03 | PRD extract | API security | The API must authenticate requests using a token. Demo secret: api_key=<SECRET_VALUE> | Engineering

## Guardrail_Test_Cases
TestCase | Data | Expected
PII-01 | <PERSON> / person name | MASK
PII-02 | <EMAIL_ADDRESS> | MASK
PII-03 | <PHONE_NUMBER> | MASK
SECRET-01 | api_key=<SECRET_VALUE> | MASK
SECRET-02 | password=<SECRET_PASSWORD> | MASK
BUSINESS-01 | PAY-101 / PAY-102 / PAY-103 | PRESERVE
BUSINESS-02 | EPIC-01 / EPIC-02 / EPIC-03 | PRESERVE
BUSINESS-03 | SAD-01 / SAD-02 / SAD-03 | PRESERVE
BUSINESS-04 | SPR-07 / SPR-08 / SPR-09 | PRESERVE
<PERSON> | Story points, dependencies, team IDs | PRESERVE