## README
Unnamed: 0 | Foreman - AI Scrum Master ¦ Synthetic Dataset (Participant Pack)
PURPOSE
This workbook is a 100% synthetic, procedurally generated dataset for the 'Foreman' hackathon. It emulates exports from an enterprise agile toolchain so your solution has realistic material to shape, sequence, forecast, and de-duplicate. No real company, customer, vendor, or personal data is included.
SOURCE-SYSTEM FICTION
- JIRA-like ALM export -> Backlog, Dependencies, Sprints, ChangeRequests, Intake_Samples
- Resource/Capacity system export -> Teams, TeamMembers, Holidays
- System Architecture Document (SAD) -> SAD_Sections
SHEETS
• Teams: Delivery teams, sprint length, base velocity.
• TeamMembers: People, roles, allocation %, capacity.
• Sprints: Sprint calendar, capacity vs committed points, status.
• Holidays: Public holidays / non-working days by team & date.
• SAD_Sections: The System Architecture Document, split into sections/layers.
• Backlog: Existing JIRA board: Epic -> Feature -> Story/Task hierarchy.
• Dependencies: Ticket-to-ticket dependency edges (the graph to sequence).
• ChangeRequests: Mid-sprint inbound asks (some duplicate existing work).
• Intake_Samples: Raw demand in several modes (one-line, PRD, notes, defect, mandate, S-AD).
• AnswerKey: HIDDEN. Catalog of seeded scenarios/anomalies - do not rely on it in code.
HOW TO USE
- Keys join across sheets: Backlog.ParentID -> Backlog.TicketID; Backlog.SADSectionID -> SAD_Sections.SectionID; Backlog.SprintID -> Sprints.SprintID; Backlog.AssigneeID -> TeamMembers.MemberID; Dependencies.From/ToTicketID -> Backlog.TicketID; ChangeRequests.PotentialDuplicateOf -> Backlog.TicketID; Sprints/TeamMembers/Holidays -> Teams.TeamID.
- Amber-shaded cells mark SEEDED issues/scenarios (a hint only). Many scenarios ONLY appear when you JOIN sheets (e.g. orphan parents, orphan dependencies, holidays inside a sprint, dependency inversion).
- Do NOT hardcode to specific record IDs. Judges may run your solution against a modified copy with different IDs and additional scenarios.
REPRODUCIBILITY
- Fixed random seed: 20260910. Regenerating with the same seed yields the same data.
- The report (Synthetic Dataset Report .docx) documents the schema and the full scenario catalog and matches this workbook exactly.

## Teams
TeamID | TeamName | Product / Service | SprintLengthDays | BaseVelocityPts | TeamSize | Timezone | DeliveryManager
TEAM-01 | Ignition Squad | VSTP - Vehicle Service Booking | 14 | 32 | 7 | CET | Isha Mone
TEAM-02 | Telemetry Guild | VSTP - Telematics Ingestion | 14 | 28 | 6 | CET | Oriol Ocon
TEAM-03 | Gateway Crew | VSTP - Integrations & APIs | 14 | 26 | 6 | IST | Kamna Sama
TEAM-04 | Cockpit Team | VSTP - Web & Mobile Frontend | 14 | 30 | 7 | IST | Praveen Chakravarthy
TEAM-05 | Sentinel Team | VSTP - Security & Release | 14 | 24 | 5 | CET | Friederike Platzek

## TeamMembers
MemberID | TeamID | Name | Role | Seniority | AllocationPct | CapacityHrsPerSprint | Location | StartDate
USR-001 | TEAM-01 | Priya Schmidt | Product Owner | Lead | 100 | 70 | Wolfsburg | 2025-01-09
USR-002 | TEAM-01 | Raghav Braun | Scrum Master | Lead | 100 | 70 | Wolfsburg | 2024-04-03
USR-003 | TEAM-01 | Lena Weber | Senior Engineer | Senior | 50 | 35 | Wolfsburg | 2025-02-11
USR-004 | TEAM-01 | Kabir Menon | Engineer | Mid | 140 | 42 | Wolfsburg | 2025-05-13
USR-005 | TEAM-01 | Arjun Braun | QA Engineer | Mid | 100 | 70 | Munich | 2024-10-08
USR-006 | TEAM-01 | Priya Nair | DevOps Engineer | Senior | 100 | 70 | Lisbon | 2024-08-05
USR-007 | TEAM-01 | Julia Kaur | UX Designer | Mid | 80 | 56 | Munich | 2025-06-02
USR-008 | TEAM-02 | Vivek Weber | Product Owner | Lead | 80 | 56 | Munich | 2024-10-13
USR-009 | TEAM-02 | Pedro Sharma | Scrum Master | Lead | 100 | 70 | Lisbon | 2024-09-22
USR-010 | TEAM-02 | Hanna Silva | Senior Engineer | Senior | 100 | 70 | Lisbon | 2024-03-07
USR-011 | TEAM-02 | Sanjay Fischer | Engineer | Mid | 100 | 70 | Munich | 2025-05-02
USR-012 | TEAM-02 | Anja Pillai | QA Engineer | Mid | 100 | 70 | Munich | 2025-06-02
USR-013 | TEAM-02 | Arjun Sharma | DevOps Engineer | Senior | 80 | 56 | Lisbon | 2025-06-11
USR-014 | TEAM-03 | Vivek Kaur | Product Owner | Lead | 100 | 70 | Chennai | 2024-11-19
USR-015 | TEAM-03 | Priya Reddy | Scrum Master | Lead | 60 | 42 | Bangalore | 2024-08-16
USR-016 | TEAM-03 | Pedro Rao | Senior Engineer | Senior | 100 | 70 | Chennai | 2024-05-19
USR-017 | TEAM-03 | Jonas Schmidt | Engineer | Mid | 100 | 70 | Chennai | 2024-02-08
USR-018 | TEAM-03 | Maja Nair | QA Engineer | Mid | 120 | 70 | Pune | 2024-03-09
USR-019 | TEAM-03 | Marta Fischer | DevOps Engineer | Senior | 100 | 70 | Chennai | 2025-05-14
USR-020 | TEAM-04 | Sofia Pinto | Product Owner | Lead | 60 | 42 | Bangalore | 2025-07-02
USR-021 | TEAM-04 | Laura Costa | Scrum Master | Lead | 100 | 70 | Bangalore | 2025-01-14
USR-022 | TEAM-04 | Sofia Menon | Senior Engineer | Senior | 100 | 70 | Chennai | 2024-11-30
USR-023 | TEAM-04 | Omar Silva | Engineer | Mid | 100 | 70 | Pune | 2024-09-07
USR-024 | TEAM-04 | Tara Pillai | QA Engineer | Mid | 100 | 70 | Chennai | 2024-09-01
USR-025 | TEAM-04 | Jonas Menon | DevOps Engineer | Senior | 60 | 42 | Bangalore | 2024-12-20
USR-026 | TEAM-04 | Tara Wagner | UX Designer | Mid | 100 | 70 | Bangalore | 2025-01-26
USR-027 | TEAM-05 | Divya Weber | Product Owner | Lead | 100 | 70 | Wolfsburg | 2024-01-12
USR-028 | TEAM-05 | Pedro Wagner | Scrum Master | Lead | 100 | 70 | Wolfsburg | 2025-05-02
USR-029 | TEAM-05 | Divya Fernandes | Senior Engineer | Senior | 50 | 35 | Wolfsburg | 2025-08-01
USR-030 | TEAM-05 | Ines Nair | Engineer | Mid | 80 | 56 | Wolfsburg | 2024-10-13
USR-031 | TEAM-05 | Noah Schmidt | QA Engineer | Mid | 100 | 70 | Lisbon | 2024-10-09

## Sprints
SprintID | TeamID | SprintName | StartDate | EndDate | WorkingDays | PlannedCapacityPts | CommittedPts | Status
SPR-01 | TEAM-01 | Sprint 1 | 2026-07-07 | 2026-07-20 | 10 | 32 | 32 | Completed
SPR-02 | TEAM-01 | Sprint 2 | 2026-07-21 | 2026-08-03 | 10 | 32 | 41 | Completed
SPR-03 | TEAM-01 | Sprint 3 | 2026-08-04 | 2026-08-17 | 10 | 32 | 75 | Active
SPR-04 | TEAM-01 | Sprint 4 | 2026-08-18 | 2026-08-31 | 10 | 32 | 42 | Planned
SPR-05 | TEAM-01 | Sprint 5 | 2026-09-01 | 2026-09-14 | 10 | 32 | 0 | Planned
SPR-06 | TEAM-01 | Sprint 6 | 2026-09-15 | 2026-09-28 | 10 | 32 | 0 | Planned
SPR-07 | TEAM-01 | Sprint 7 | 2026-09-29 | 2026-10-12 | 10 | 32 | 0 | Planned
SPR-08 | TEAM-01 | Sprint 8 | 2026-10-13 | 2026-10-26 | 10 | 32 | 0 | Planned
SPR-09 | TEAM-01 | Sprint 9 | 2026-10-27 | 2026-11-09 | 10 | 32 | 0 | Planned
SPR-10 | TEAM-01 | Sprint 10 | 2026-11-10 | 2026-11-23 | 10 | 32 | 0 | Planned

## Holidays
HolidayID | Location | Date | HolidayName | ImpactedTeamID
HOL-01 | Germany | 2026-07-15 | Regional Holiday | TEAM-01
HOL-02 | Germany | 2026-08-15 | Assumption Day | TEAM-02
HOL-03 | India | 2026-08-15 | Independence Day | TEAM-03
HOL-04 | India | 2026-08-15 | Independence Day | TEAM-04
HOL-05 | Portugal | 2026-08-20 | Local Holiday | TEAM-05
HOL-06 | India | 2026-09-05 | Regional Festival | TEAM-04
HOL-07 | Germany | 2026-10-03 | Unity Day | TEAM-01
HOL-08 | India | 2026-10-02 | Gandhi Jayanti | TEAM-03
HOL-09 | Germany | 2026-10-03 | Unity Day | TEAM-05
HOL-10 | Portugal | 2026-10-05 | Republic Day | TEAM-05

## SAD_Sections
SectionID | SADTitle | SectionNumber | SectionTitle | ArchitectureLayer | Summary
SAD-01 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 2.1 | Cloud Landing Zone & Networking | Infrastructure | AWS multi-account landing zone, VPCs, subnets, transit gateway, tagging policy.
SAD-02 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 2.2 | Identity & Access Management | Identity | Customer + workforce identity via IdP, OAuth2/OIDC, RBAC, token services.
SAD-03 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 3.1 | Data Platform & Lake | Data | Ingestion, raw/curated zones, schema registry, batch + stream pipelines.
SAD-04 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 3.2 | Telematics Streaming | Data | Vehicle signal ingestion (MQTT), stream processing, device registry.
SAD-05 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 4.1 | Booking Core Services | Backend | Service booking, scheduling, availability, pricing microservices.
SAD-06 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 4.2 | Workshop & Resource Services | Backend | Workshop slots, technician allocation, parts availability services.
SAD-07 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 5.1 | External Integrations | Integrations | Dealer DMS, payment gateway, parts supplier, notification (SMS/email).
SAD-08 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 5.2 | Event & Messaging Backbone | Integrations | Event bus, dead-letter handling, idempotency, saga orchestration.
SAD-09 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 6.1 | Customer Web Portal | Frontend | Responsive web app for booking, tracking, history.
SAD-10 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 6.2 | Mobile & Service Advisor App | Frontend | Mobile app + service-advisor cockpit.
SAD-11 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 7.1 | Quality Engineering & Test Automation | QA | Test strategy, automation harness, performance & contract tests.
SAD-12 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 8.1 | Security, Privacy & Compliance | Security | Threat model, GDPR data handling, secrets, audit logging, pen-test.
SAD-13 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 9.1 | Observability & SRE | Security | Logging, metrics, tracing, alerting, SLOs, runbooks.
SAD-14 | VSTP - Vehicle Service Booking & Telematics Platform S-AD v1.3 | 10.1 | CI/CD & Release Management | Release | Pipelines, IaC, environment promotion, blue-green release, rollback.

## Backlog
TicketID | Type | Title | ParentID | SADSectionID | Layer | StoryPoints | Priority | Status | SprintID | AssigneeID | HasAcceptanceCriteria | HasDoD | Labels | CreatedDate
EPIC-01 | Epic | Cloud Landing Zone |  | SAD-01 | Infrastructure |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-04
EPIC-02 | Epic | Identity & Access |  | SAD-02 | Identity |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-23
EPIC-03 | Epic | Data Platform |  | SAD-03 | Data |  | Highest | In Progress |  |  | Y | Y | epic | 2026-07-07
EPIC-04 | Epic | Telematics Streaming |  | SAD-04 | Data |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-07
EPIC-05 | Epic | Booking Core |  | SAD-05 | Backend |  | Highest | In Progress |  |  | Y | Y | epic | 2026-07-08
EPIC-06 | Epic | Workshop Services |  | SAD-06 | Backend |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-08
EPIC-07 | Epic | External Integrations |  | SAD-07 | Integrations |  | Highest | In Progress |  |  | Y | Y | epic | 2026-07-05
EPIC-08 | Epic | Event Backbone |  | SAD-08 | Integrations |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-27
EPIC-09 | Epic | Customer Web Portal |  | SAD-09 | Frontend |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-06
EPIC-10 | Epic | Mobile & Advisor App |  | SAD-10 | Frontend |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-11
EPIC-11 | Epic | Quality Engineering |  | SAD-11 | QA |  | Highest | In Progress |  |  | Y | Y | epic | 2026-07-08
EPIC-12 | Epic | Security & Compliance |  | SAD-12 | Security |  | Highest | In Progress |  |  | Y | Y | epic | 2026-07-03
EPIC-13 | Epic | CI/CD & Release |  | SAD-14 | Release |  | Highest | In Progress |  |  | Y | Y | epic | 2026-07-07
F-01 | Feature | VPC & Networking | EPIC-01 | SAD-01 | Infrastructure |  | High | In Progress |  |  | Y | Y | feature | 2026-06-14
T-100 | Story | Build subnet layout | F-01 | SAD-01 | Infrastructure | 13.0 | High | In Progress | SPR-03 | USR-004 | Y | Y | infra | 2026-06-23
T-101 | Story | Integrate baseline VPC | F-01 | SAD-01 | Infrastructure | 8.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-29
T-102 | Task | Document baseline VPC | F-01 | SAD-01 | Infrastructure | 3.0 | High | To Do |  |  | Y | Y | qa | 2026-06-26
T-103 | Story | Harden tagging policy | F-01 | SAD-01 | Infrastructure | 5.0 | High | Done | SPR-02 | USR-002 | Y | Y | ui | 2026-07-01
F-02 | Feature | Account Baseline & Tagging | EPIC-01 | SAD-01 | Infrastructure |  | High | In Progress |  |  | Y | Y | feature | 2026-07-11
T-104 | Story | Document transit gateway | F-02 | SAD-01 | Infrastructure | 3.0 | Medium | To Do |  |  | N | N | ui | 2026-06-22
T-105 | Story | Integrate baseline VPC | F-02 | SAD-01 | Infrastructure | 13.0 | High | To Do |  |  | Y | Y | sec | 2026-07-04
T-106 | Task | Automate shared VPC endpoints | F-02 | SAD-01 | Infrastructure | 3.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-02
T-107 | Story | Integrate subnet layout | F-02 | SAD-01 | Infrastructure | 8.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-30
F-03 | Feature | Shared Services | EPIC-01 | SAD-01 | Infrastructure |  | High | In Progress |  |  | Y | Y | feature | 2026-07-03
T-108 | Story | Build shared VPC endpoints | F-03 | SAD-01 | Infrastructure | 8.0 | Medium | To Do |  |  | Y | Y | ui | 2026-07-06
T-109 | Story | Configure shared VPC endpoints | F-03 | SAD-01 | Infrastructure | 8.0 | Low | To Do |  |  | Y | Y | infra | 2026-07-08
F-04 | Feature | IdP & OAuth Setup | EPIC-02 | SAD-02 | Identity |  | High | In Progress |  |  | Y | Y | feature | 2026-07-01
T-110 | Story | Automate user pool | F-04 | SAD-02 | Identity | 2.0 | Medium | To Do |  |  | Y | Y | sec | 2026-06-10
T-111 | Story | Build token refresh flow | F-04 | SAD-02 | Identity | 5.0 | High | To Do |  |  | Y | Y | qa | 2026-07-04
F-05 | Feature | RBAC & Roles | EPIC-02 | SAD-02 | Identity |  | High | In Progress |  |  | Y | Y | feature | 2026-06-11
T-112 | Story | Implement RBAC roles | F-05 | SAD-02 | Identity | 8.0 | Low | To Do |  |  | Y | Y | qa | 2026-06-27
T-113 | Story | Build RBAC roles | F-05 | SAD-02 | Identity | 8.0 | Medium | To Do |  |  | Y | Y | ui | 2026-06-10
T-114 | Task | Build user pool | F-05 | SAD-02 | Identity | 5.0 | Low | Done | SPR-01 | USR-005 | Y | Y | sec | 2026-06-13
F-06 | Feature | Token & Session Services | EPIC-02 | SAD-02 | Identity |  | High | In Progress |  |  | Y | Y | feature | 2026-06-03
T-115 | Story | Provision OIDC client | F-06 | SAD-02 | Identity | 0.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-04
T-116 | Story | Configure RBAC roles | F-06 | SAD-02 | Identity | 8.0 | Low | To Do | SPR-04 | USR-002 | Y | Y | backend | 2026-07-01
F-07 | Feature | Ingestion Pipelines | EPIC-03 | SAD-03 | Data |  | High | In Progress |  |  | Y | Y | feature | 2026-06-09
T-117 | Story | Test schema registry | F-07 | SAD-03 | Data | 13.0 | High | To Do |  |  | Y | Y | qa | 2026-06-26
T-118 | Story | Automate stream consumer | F-07 | SAD-03 | Data | 0.0 | Low | To Do |  |  | Y | Y | backend | 2026-07-07
F-08 | Feature | Curated Data Zone | EPIC-03 | SAD-03 | Data |  | High | In Progress |  |  | Y | Y | feature | 2026-06-26
T-119 | Story | Integrate schema registry | F-08 | SAD-03 | Data | 8.0 | High | To Do |  |  | Y | Y | backend | 2026-06-17
T-120 | Story | Automate schema registry | F-08 | SAD-03 | Data | 3.0 | Medium | To Do |  |  | Y | Y | ui | 2026-07-07
F-09 | Feature | Schema Registry | EPIC-03 | SAD-03 | Data |  | High | In Progress |  |  | Y | Y | feature | 2026-06-28
T-121 | Story | Build schema registry | F-09 | SAD-03 | Data | 8.0 | Medium | To Do |  |  | Y | Y | qa | 2026-07-04
T-122 | Story | Provision ingestion job | F-09 | SAD-03 | Data | 8.0 | Medium | To Do |  |  | Y | Y | ui | 2026-06-24
F-10 | Feature | Device Registry | EPIC-04 | SAD-04 | Data |  | High | In Progress |  |  | Y | Y | feature | 2026-07-09
T-123 | Story | Harden device registry API | F-10 | SAD-04 | Data | 8.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-15
T-124 | Story | Integrate device registry API | F-10 | SAD-04 | Data | 5.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-28
F-11 | Feature | Stream Processing | EPIC-04 | SAD-04 | Data |  | High | In Progress |  |  | Y | Y | feature | 2026-07-08
T-125 | Story | Implement ingestion job | F-11 | SAD-04 | Data | 13.0 | High | In Progress | SPR-03 | USR-006 | Y | Y | ui | 2026-06-21
T-126 | Story | Document device registry API | F-11 | SAD-04 | Data | 5.0 | Low | To Do |  |  | Y | Y | qa | 2026-06-14
F-12 | Feature | Signal Storage | EPIC-04 | SAD-04 | Data |  | High | In Progress |  |  | Y | Y | feature | 2026-06-10
T-127 | Story | Design curated table | F-12 | SAD-04 | Data | 3.0 | High | To Do |  |  | Y | Y | infra | 2026-06-17
T-128 | Story | Automate ingestion job | F-12 | SAD-04 | Data | 5.0 | High | To Do |  |  | Y | Y | sec | 2026-06-17
T-129 | Task | Configure stream consumer | F-12 | SAD-04 | Data | 13.0 | High | To Do |  |  | Y | Y | backend | 2026-06-19
T-130 | Story | Harden stream consumer | F-12 | SAD-04 | Data | 8.0 | Medium | To Do |  |  | Y | Y | ui | 2026-06-06
F-13 | Feature | Booking Service | EPIC-05 | SAD-05 | Backend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-07
T-131 | Story | Provision scheduling logic | F-13 | SAD-05 | Backend | 3.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-10
T-132 | Story | Integrate workshop slot API | F-13 | SAD-05 | Backend | 8.0 | Medium | To Do | SPR-04 | USR-007 | Y | Y | backend | 2026-06-23
T-133 | Task | Implement availability service | F-13 | SAD-05 | Backend | 8.0 | High | To Do |  |  | Y | Y | ui | 2026-06-04
T-134 | Story | Harden scheduling logic | F-13 | SAD-05 | Backend | 3.0 | High | To Do |  |  | Y | Y | backend | 2026-06-10
F-14 | Feature | Scheduling Engine | EPIC-05 | SAD-05 | Backend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-04
T-135 | Story | Design pricing rules | F-14 | SAD-05 | Backend | 3.0 | High | To Do |  |  | Y | Y | backend | 2026-06-16
T-136 | Story | Provision workshop slot API | F-14 | SAD-05 | Backend | 3.0 | Low | To Do |  |  | Y | Y | ui | 2026-06-22
T-137 | Task | Provision workshop slot API | F-14 | SAD-05 | Backend | 3.0 | High | To Do |  |  | Y | Y | infra | 2026-06-22
T-138 | Story | Automate pricing rules | F-14 | SAD-05 | Backend | 3.0 | Low | To Do |  |  | N | N | backend | 2026-06-29
F-15 | Feature | Pricing Service | EPIC-05 | SAD-05 | Backend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-11
T-139 | Story | Provision availability service | F-15 | SAD-05 | Backend | 0.0 | Medium | To Do |  |  | Y | Y | ui | 2026-06-09
T-140 | Story | Test availability service | F-15 | SAD-05 | Backend | 5.0 | Medium | To Do |  |  | Y | Y | sec | 2026-07-05
F-16 | Feature | Workshop Slots | EPIC-06 | SAD-06 | Backend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-06
T-141 | Story | Document availability service | F-16 | SAD-06 | Backend | 0.0 | High | To Do |  |  | Y | Y | backend | 2026-07-02
T-142 | Story | Build workshop slot API | F-16 | SAD-06 | Backend | 3.0 | Low | To Do |  |  | Y | Y | backend | 2026-06-19
T-143 | Task | Automate CRUD API | F-16 | SAD-06 | Backend | 3.0 | Medium | To Do |  |  | Y | Y | sec | 2026-07-07
T-144 | Story | Automate workshop slot API | F-16 | SAD-06 | Backend | 13.0 | High | To Do |  |  | Y | Y | sec | 2026-06-01
F-17 | Feature | Technician Allocation | EPIC-06 | SAD-06 | Backend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-25
T-145 | Story | Integrate workshop slot API | F-17 | SAD-06 | Backend | 3.0 | High | Done | SPR-01 | USR-004 | N | N | sec | 2026-07-06
T-146 | Story | Automate CRUD API | F-17 | SAD-06 | Backend | 8.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-30
F-18 | Feature | Parts Availability | EPIC-06 | SAD-06 | Backend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-19
T-147 | Story | Design workshop slot API | F-18 | SAD-06 | Backend | 3.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-10
T-148 | Story | Implement scheduling logic | F-18 | SAD-06 | Backend | 5.0 | High | To Do |  |  | Y | Y | ui | 2026-07-11
T-149 | Task | Provision availability service | F-18 | SAD-06 | Backend | 13.0 | Low | To Do |  |  | Y | Y | qa | 2026-06-15
F-19 | Feature | Payment Gateway | EPIC-07 | SAD-07 | Integrations |  | High | In Progress |  |  | Y | Y | feature | 2026-06-29
T-150 | Story | Provision DMS connector | F-19 | SAD-07 | Integrations | 13.0 | Medium | To Do |  |  | N | N | qa | 2026-06-01
T-151 | Story | Test saga handler | F-19 | SAD-07 | Integrations | 3.0 | Medium | To Do |  |  | Y | Y | qa | 2026-07-06
T-152 | Task | Integrate retry & DLQ | F-19 | SAD-07 | Integrations | 13.0 | Low | Done | SPR-02 | USR-001 | Y | Y | ui | 2026-07-02
T-153 | Story | Test saga handler | F-19 | SAD-07 | Integrations | 8.0 | Low | To Do |  |  | Y | Y | backend | 2026-07-02
F-20 | Feature | Dealer DMS Connector | EPIC-07 | SAD-07 | Integrations |  | High | In Progress |  |  | Y | Y | feature | 2026-06-16
T-154 | Story | Design event publisher | F-20 | SAD-07 | Integrations | 8.0 | Low | To Do |  |  | N | Y | ui | 2026-06-21
T-155 | Story | Harden retry & DLQ | F-20 | SAD-07 | Integrations | 3.0 | Medium | To Do |  |  | Y | Y | infra | 2026-07-03
T-156 | Task | Configure retry & DLQ | F-20 | SAD-07 | Integrations | 13.0 | Medium | To Do |  |  | Y | Y | sec | 2026-06-09
F-21 | Feature | Notification Service | EPIC-07 | SAD-07 | Integrations |  | High | In Progress |  |  | Y | Y | feature | 2026-06-20
T-157 | Story | Design retry & DLQ | F-21 | SAD-07 | Integrations | 8.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-20
T-158 | Story | Test payment adapter | F-21 | SAD-07 | Integrations | 3.0 | High | Done | SPR-01 | USR-003 | Y | Y | ui | 2026-06-04
T-159 | Task | Design retry & DLQ | F-21 | SAD-07 | Integrations | 3.0 | Medium | Done | SPR-02 | USR-003 | Y | Y | backend | 2026-06-29
F-22 | Feature | Event Bus | EPIC-08 | SAD-08 | Integrations |  | High | In Progress |  |  | Y | Y | feature | 2026-06-23
T-160 | Story | Provision saga handler | F-22 | SAD-08 | Integrations | 13.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-16
T-161 | Story | Build saga handler | F-22 | SAD-08 | Integrations | 13.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-06
T-162 | Task | Document retry & DLQ | F-22 | SAD-08 | Integrations | 8.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-07
T-163 | Story | Integrate retry & DLQ | F-22 | SAD-08 | Integrations | 13.0 | Medium | In Progress | SPR-03 | USR-003 | Y | Y | qa | 2026-07-04
F-23 | Feature | Saga Orchestration | EPIC-08 | SAD-08 | Integrations |  | High | In Progress |  |  | Y | Y | feature | 2026-06-25
T-164 | Story | Implement saga handler | F-23 | SAD-08 | Integrations | 13.0 | Medium | Done | SPR-01 | USR-004 | Y | Y | qa | 2026-06-03
T-165 | Story | Build event publisher | F-23 | SAD-08 | Integrations | 5.0 | Medium | To Do |  |  | Y | Y | sec | 2026-06-14
F-24 | Feature | Dead-letter Handling | EPIC-08 | SAD-08 | Integrations |  | High | In Progress |  |  | Y | Y | feature | 2026-07-11
T-166 | Story | Automate DMS connector | F-24 | SAD-08 | Integrations | 8.0 | Low | To Do |  |  | Y | Y | qa | 2026-06-11
T-167 | Story | Integrate saga handler | F-24 | SAD-08 | Integrations | 2.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-19
T-168 | Task | Harden payment adapter | F-24 | SAD-08 | Integrations | 3.0 | High | To Do |  |  | Y | Y | backend | 2026-06-29
F-25 | Feature | Booking Web UI | EPIC-09 | SAD-09 | Frontend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-17
T-169 | Story | Test push handler | F-25 | SAD-09 | Frontend | 13.0 | Medium | In Progress | SPR-03 | USR-007 | Y | Y | sec | 2026-06-10
T-170 | Story | Build booking screen | F-25 | SAD-09 | Frontend | 3.0 | Low | To Do |  |  | Y | Y | qa | 2026-06-07
T-171 | Task | Configure advisor dashboard | F-25 | SAD-09 | Frontend | 13.0 | Medium | Done | SPR-02 | USR-001 | Y | Y | ui | 2026-07-07
F-26 | Feature | Tracking & History | EPIC-09 | SAD-09 | Frontend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-30
T-172 | Story | Implement push handler | F-26 | SAD-09 | Frontend | 13.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-04
T-173 | Story | Implement advisor dashboard | F-26 | SAD-09 | Frontend | 5.0 | Low | Done | SPR-02 | USR-005 | Y | Y | infra | 2026-07-11
T-174 | Task | Test tracking view | F-26 | SAD-09 | Frontend | 3.0 | High | To Do |  |  | Y | Y | ui | 2026-06-05
T-175 | Story | Document booking screen | F-26 | SAD-09 | Frontend | 3.0 | Medium | Done | SPR-01 | USR-005 | Y | Y | sec | 2026-06-19
F-27 | Feature | Account Pages | EPIC-09 | SAD-09 | Frontend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-24
T-176 | Story | Automate account page | F-27 | SAD-09 | Frontend | 2.0 | Low | To Do |  |  | Y | Y | backend | 2026-06-03
T-177 | Story | Configure account page | F-27 | SAD-09 | Frontend | 3.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-11
T-178 | Task | Automate advisor dashboard | F-27 | SAD-09 | Frontend | 3.0 | Low | To Do |  |  | Y | Y | ui | 2026-06-13
F-28 | Feature | Mobile Booking | EPIC-10 | SAD-10 | Frontend |  | High | In Progress |  |  | Y | Y | feature | 2026-06-28
T-179 | Story | Build advisor dashboard | F-28 | SAD-10 | Frontend | 13.0 | Medium | To Do |  |  | Y | Y | ui | 2026-06-03
T-180 | Story | Configure push handler | F-28 | SAD-10 | Frontend | 2.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-13
F-29 | Feature | Advisor Cockpit | EPIC-10 | SAD-10 | Frontend |  | High | In Progress |  |  | Y | Y | feature | 2026-07-04
T-181 | Story | Design tracking view | F-29 | SAD-10 | Frontend | 13.0 | High | To Do |  |  | Y | Y | sec | 2026-06-01
T-182 | Story | Provision advisor dashboard | F-29 | SAD-10 | Frontend | 8.0 | High | To Do |  |  | Y | Y | infra | 2026-06-05
T-183 | Task | Test booking screen | F-29 | SAD-10 | Frontend | 5.0 | Low | To Do |  |  | Y | Y | sec | 2026-06-13
F-30 | Feature | Push Notifications | EPIC-10 | SAD-10 | Frontend |  | High | In Progress |  |  | Y | Y | feature | 2026-07-04
T-184 | Story | Document tracking view | F-30 | SAD-10 | Frontend | 13.0 | Medium | To Do | SPR-04 | USR-001 | Y | Y | infra | 2026-06-09
T-185 | Story | Integrate advisor dashboard | F-30 | SAD-10 | Frontend | 8.0 | Medium | To Do |  |  | Y | Y | infra | 2026-07-05
T-186 | Task | Provision account page | F-30 | SAD-10 | Frontend | 3.0 | Medium | To Do |  |  | Y | Y | sec | 2026-06-23
F-31 | Feature | Test Automation Harness | EPIC-11 | SAD-11 | QA |  | High | In Progress |  |  | Y | Y | feature | 2026-06-22
T-187 | Story | Automate perf test suite | F-31 | SAD-11 | QA | 5.0 | Low | To Do |  |  | Y | Y | ui | 2026-06-16
T-188 | Story | Test test harness | F-31 | SAD-11 | QA | 8.0 | Low | To Do |  |  | Y | Y | sec | 2026-06-30
F-32 | Feature | Performance Tests | EPIC-11 | SAD-11 | QA |  | High | In Progress |  |  | Y | Y | feature | 2026-06-10
T-189 | Story | Provision regression pack | F-32 | SAD-11 | QA | 5.0 | Medium | To Do |  |  | Y | Y | sec | 2026-06-11
T-190 | Story | Document test data factory | F-32 | SAD-11 | QA | 3.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-22
T-191 | Task | Automate contract test | F-32 | SAD-11 | QA | 3.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-19
F-33 | Feature | Contract Tests | EPIC-11 | SAD-11 | QA |  | High | In Progress |  |  | Y | Y | feature | 2026-06-23
T-192 | Story | Automate contract test | F-33 | SAD-11 | QA | 3.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-30
T-193 | Story | Harden test data factory | F-33 | SAD-11 | QA | 8.0 | Medium | To Do |  |  | Y | Y | ui | 2026-06-18
T-194 | Task | Automate test harness | F-33 | SAD-11 | QA | 5.0 | Low | To Do |  |  | Y | Y | ui | 2026-06-15
T-195 | Story | Test contract test | F-33 | SAD-11 | QA | 8.0 | High | To Do |  |  | N | N | backend | 2026-06-06
F-34 | Feature | Threat Model & Hardening | EPIC-12 | SAD-12 | Security |  | High | In Progress |  |  | Y | Y | feature | 2026-06-05
T-196 | Story | Document pen-test fixes | F-34 | SAD-12 | Security | 3.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-16
T-197 | Story | Harden GDPR erasure flow | F-34 | SAD-12 | Security | 5.0 | Low | To Do |  |  | Y | Y | ui | 2026-06-25
T-198 | Task | Harden audit log sink | F-34 | SAD-12 | Security | 2.0 | Low | To Do |  |  | Y | Y | ui | 2026-06-12
F-35 | Feature | GDPR Data Handling | EPIC-12 | SAD-12 | Security |  | High | In Progress |  |  | Y | Y | feature | 2026-06-04
T-199 | Story | Provision GDPR erasure flow | F-35 | SAD-12 | Security | 3.0 | Medium | To Do |  |  | Y | Y | sec | 2026-06-22
T-200 | Story | Harden GDPR erasure flow | F-35 | SAD-12 | Security | 5.0 | Low | To Do |  |  | Y | Y | backend | 2026-06-29
T-201 | Task | Test audit log sink | F-35 | SAD-12 | Security | 3.0 | Medium | To Do |  |  | Y | Y | qa | 2026-06-03
F-36 | Feature | Audit Logging | EPIC-12 | SAD-12 | Security |  | High | In Progress |  |  | Y | Y | feature | 2026-06-30
T-202 | Story | Integrate audit log sink | F-36 | SAD-12 | Security | 8.0 | Low | In Progress | SPR-03 | USR-003 | Y | Y | infra | 2026-06-18
T-203 | Story | Harden threat model | F-36 | SAD-12 | Security | 3.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-15
F-37 | Feature | CI Pipeline | EPIC-13 | SAD-14 | Release |  | High | In Progress |  |  | Y | Y | feature | 2026-07-09
T-204 | Story | Design IaC module | F-37 | SAD-14 | Release | 3.0 | Medium | To Do |  |  | Y | Y | infra | 2026-06-18
T-205 | Story | Provision blue-green deploy | F-37 | SAD-14 | Release | 8.0 | Low | To Do |  |  | Y | Y | ui | 2026-07-03
T-206 | Task | Design promotion gate | F-37 | SAD-14 | Release | 2.0 | High | Done | SPR-01 | USR-007 | Y | Y | qa | 2026-06-29
T-207 | Story | Integrate rollback runbook | F-37 | SAD-14 | Release | 3.0 | High | Done | SPR-01 | USR-004 | Y | Y | ui | 2026-07-02
F-38 | Feature | IaC & Environments | EPIC-13 | SAD-14 | Release |  | High | In Progress |  |  | Y | Y | feature | 2026-07-07
T-208 | Story | Document CI pipeline | F-38 | SAD-14 | Release | 13.0 | Low | To Do |  |  | Y | Y | sec | 2026-07-01
T-209 | Story | Document CI pipeline | F-38 | SAD-14 | Release | 2.0 | Medium | To Do |  |  | Y | Y | ui | 2026-07-03
T-210 | Task | Integrate rollback runbook | F-38 | SAD-14 | Release | 3.0 | Medium | To Do |  |  | Y | Y | backend | 2026-06-26
F-39 | Feature | Blue-Green Release | EPIC-13 | SAD-14 | Release |  | High | In Progress |  |  | Y | Y | feature | 2026-06-08
T-211 | Story | Provision CI pipeline | F-39 | SAD-14 | Release | 2.0 | Low | Done | SPR-02 | USR-002 | Y | Y | backend | 2026-06-11
T-212 | Story | Test CI pipeline | F-39 | SAD-14 | Release | 13.0 | Medium | To Do | SPR-04 | USR-001 | Y | Y | sec | 2026-06-18
T-213 | Task | Implement promotion gate | F-39 | SAD-14 | Release | 3.0 | Low | To Do |  |  | Y | Y | sec | 2026-06-12
T-214 | Story | Configure promotion gate | F-99 | SAD-03 | Release | 5.0 | Low | To Do |  |  | Y | Y | qa
T-215 | Story | Automate rollback runbook | EPIC-77 | SAD-07 | Release | 2.0 | High | In Progress | SPR-03 | USR-005 | Y | Y | ui
T-216 | Story | Document tagging policy | F-88 | SAD-02 | Infrastructure | 5.0 | Medium | To Do |  |  | Y | Y | backend
EPIC-14 | Epic | Loyalty & Rewards (unscoped) |  | SAD-99 | Backend |  | Highest | In Progress |  |  | Y | Y | epic | 2026-06-06
T-217 | Story | Add tests for schema registry | F-07 | SAD-03 | Data | 13.0 | High | In Progress | SPR-03 | USR-005 | Y | Y | qa | 2026-07-06

## Dependencies
DependencyID | FromTicketID | ToTicketID (depends on) | DependencyType | Notes
DEP-001 | T-205 | T-136 | Blocks | Release work needs Backend in place
DEP-002 | T-179 | T-216 | Blocks | Frontend work needs Infrastructure in place
DEP-003 | T-182 | T-145 | Blocks | Frontend work needs Backend in place
DEP-004 | T-191 | T-146 | Blocks | QA work needs Backend in place
DEP-005 | T-165 | T-148 | Blocks | Integrations work needs Backend in place
DEP-006 | T-200 | T-119 | Blocks | Security work needs Data in place
DEP-007 | T-199 | T-163 | Blocks | Security work needs Integrations in place
DEP-008 | T-172 | T-106 | Blocks | Frontend work needs Infrastructure in place
DEP-009 | T-199 | T-105 | Blocks | Security work needs Infrastructure in place
DEP-010 | T-195 | T-170 | Blocks | QA work needs Frontend in place
DEP-011 | T-192 | T-181 | Blocks | QA work needs Frontend in place
DEP-012 | T-188 | T-145 | Blocks | QA work needs Backend in place
DEP-013 | T-134 | T-112 | Blocks | Backend work needs Identity in place
DEP-014 | T-205 | T-169 | Blocks | Release work needs Frontend in place
DEP-015 | T-215 | T-185 | Blocks | Release work needs Frontend in place
DEP-016 | T-157 | T-117 | Blocks | Integrations work needs Data in place
DEP-017 | T-183 | T-114 | Blocks | Frontend work needs Identity in place
DEP-018 | T-159 | T-133 | Blocks | Integrations work needs Backend in place
DEP-019 | T-202 | T-101 | Blocks | Security work needs Infrastructure in place
DEP-020 | T-136 | T-111 | Blocks | Backend work needs Identity in place
DEP-021 | T-162 | T-9999 | Blocks | references missing ticket
DEP-022 | T-183 | T-110 | Blocks | part of a dependency cycle
DEP-023 | T-110 | T-188 | Blocks | part of a dependency cycle
DEP-024 | T-188 | T-183 | Blocks | part of a dependency cycle
DEP-025 | T-164 | T-169 | Blocks | scheduled before its dependency

## ChangeRequests
CRID | ReceivedDate | Source | RawText | SuggestedType | PotentialDuplicateOf | TargetSprintID | Status
CR-001 | 2026-08-04 | Workshop note | Add SMS reminder 24h before service appointment | Story |  | SPR-04 | New
CR-002 | 2026-08-04 | Workshop note | Support Apple Pay at checkout | Story |  | SPR-05 | New
CR-003 | 2026-07-20 | Stakeholder email | GDPR: allow customer to export their booking history | Story |  | SPR-04 | New
CR-004 | 2026-08-01 | Compliance mandate | Show technician ETA on tracking screen | Story |  | SPR-04 | New
CR-005 | 2026-07-31 | Security finding | Bulk-import dealer service catalog | Story |  | SPR-04 | New
CR-006 | 2026-07-22 | Compliance mandate | Add rate-limiting to public booking API | Story |  | SPR-03 | New
CR-007 | 2026-07-30 | Workshop note | Multi-language support for German and Portuguese | Story |  | SPR-04 | New
CR-008 | 2026-07-30 | Workshop note | Alert when telematics device stops reporting | Story |  | SPR-05 | New
CR-009 | 2026-08-02 | Dealer feedback | Please add tests for schema registry (requested again) | Story | T-217 | SPR-03 | Needs triage
CR-010 | 2026-07-25 | Stakeholder email | Please automate workshop slot api (requested again) | Story | T-144 | SPR-04 | Needs triage
CR-011 | 2026-07-25 | Support escalation | Please implement advisor dashboard (requested again) | Story | T-173 | SPR-05 | Needs triage
CR-012 | 2026-08-02 | Support escalation | Customers want a text message before their appointment | Story | CR-001 | SPR-04 | Needs triage

## Intake_Samples
IntakeID | IntakeMode | Title | RawContent | SourceStakeholder
INT-01 | One-line ask | Faster service booking | Make it possible for a customer to book a service in under two minutes. | Head of Aftersales
INT-02 | PRD extract | Booking & scheduling PRD | The platform shall allow customers to select a dealer, choose a service package, view available slots, and confirm a booking. It must support rescheduling and cancellation, send confirmations, and expose availability from workshop systems in near real-time. | Product Management
INT-03 | Workshop notes | Discovery workshop transcript | Dealers said double-booking is the #1 pain. Technicians want to see parts availability before accepting a job. Customers abandon booking when they cannot see price up front. | Facilitator
INT-04 | Defect trend | Q2 defect analysis | 37% of production incidents trace to payment timeouts and missing idempotency on retries. Recommend hardening the payment integration and event backbone. | QA Lead
INT-05 | Compliance mandate | GDPR & data residency | All customer PII must remain in EU regions. Customers must be able to request export and erasure of their data within 30 days. Audit logging is mandatory for all data access. | DPO / Legal
INT-06 | Full S-AD | VSTP System Architecture Document | See SAD_Sections sheet for the full sectioned architecture (SAD-01 .. SAD-14) covering landing zone, identity, data platform, telematics, booking & workshop services, integrations, event backbone, web & mobile frontends, quality engineering, security & compliance, observability, and CI/CD. | Chief Architect

## AnswerKey
ScenarioID | Category | Location | Description | WhyItMatters | DetectionHint
MBR-OVERALLOC-USR-004 | Capacity / Over-allocation | TeamMembers!F5 | Kabir Menon (USR-004) allocated at 140% (>100%). | Capacity forecasts overstate available effort; Scrum Master should flag unrealistic allocation. | Filter TeamMembers.AllocationPct > 100.
MBR-OVERALLOC-USR-018 | Capacity / Over-allocation | TeamMembers!F19 | Maja Nair (USR-018) allocated at 120% (>100%). | Capacity forecasts overstate available effort; Scrum Master should flag unrealistic allocation. | Filter TeamMembers.AllocationPct > 100.
OVERCOMMIT-SPR-02 | Capacity / Over-committed sprint | Sprints!SPR-02 | SPR-02 committed 41 pts against capacity 32 pts. | Over-commitment predicts spillover; Scrum Master should rebalance before sprint start. | Compare Sprints.CommittedPts vs PlannedCapacityPts (or sum Backlog points per SprintID).
OVERCOMMIT-SPR-03 | Capacity / Over-committed sprint | Sprints!SPR-03 | SPR-03 committed 75 pts against capacity 32 pts. | Over-commitment predicts spillover; Scrum Master should rebalance before sprint start. | Compare Sprints.CommittedPts vs PlannedCapacityPts (or sum Backlog points per SprintID).
OVERCOMMIT-SPR-04 | Capacity / Over-committed sprint | Sprints!SPR-04 | SPR-04 committed 42 pts against capacity 32 pts. | Over-commitment predicts spillover; Scrum Master should rebalance before sprint start. | Compare Sprints.CommittedPts vs PlannedCapacityPts (or sum Backlog points per SprintID).
CAP-HOLIDAY-SPR-01 | Capacity / Unreflected holiday | Holidays!HOL-01 vs Sprints!SPR-01 | HOL-01 (2026-07-15) falls inside SPR-01 (07-Jul..20-Jul) for TEAM-01 but PlannedCapacityPts is unchanged. | A day lost to holidays lowers real capacity; a good forecaster joins Holidays to Sprints by date range. | Join Holidays.Date within [Sprints.StartDate, Sprints.EndDate] for the same TeamID.
CR-DUP-CR-009 | Change-request duplicate | ChangeRequests!CR-009 | CR-009 duplicates existing backlog ticket T-217 'Add tests for schema registry'. | Core mid-sprint capability: detect the incoming ask already exists before creating a new ticket. | Semantic match ChangeRequests.RawText against Backlog.Title; PotentialDuplicateOf holds the truth.
CR-DUP-CR-010 | Change-request duplicate | ChangeRequests!CR-010 | CR-010 duplicates existing backlog ticket T-144 'Automate workshop slot API'. | Core mid-sprint capability: detect the incoming ask already exists before creating a new ticket. | Semantic match ChangeRequests.RawText against Backlog.Title; PotentialDuplicateOf holds the truth.
CR-DUP-CR-011 | Change-request duplicate | ChangeRequests!CR-011 | CR-011 duplicates existing backlog ticket T-173 'Implement advisor dashboard'. | Core mid-sprint capability: detect the incoming ask already exists before creating a new ticket. | Semantic match ChangeRequests.RawText against Backlog.Title; PotentialDuplicateOf holds the truth.
CR-DUP-CR-012 | Change-request duplicate (intra-intake) | ChangeRequests!CR-012 | CR-012 restates CR-001 (SMS reminder) in different words. | Two inbound asks in the same intake are the same need; must be merged, not double-created. | Compare change requests to EACH OTHER, not only to the backlog.
DEP-CYCLE-1 | Circular dependency | Dependencies!T-183->T-110->T-188->T-183 | Cycle detected: T-183 -> T-110 -> T-188 -> T-183. | A cycle makes topological sprint sequencing impossible; must be detected and broken. | Run cycle detection on the Dependencies graph (FromTicketID -> ToTicketID).
DEP-INVERSION-DEP-025 | Dependency inversion / out-of-order plan | Dependencies!DEP-025 | T-164 (Sprint 1) depends on T-169 (Sprint 3) - dependency is scheduled AFTER the dependent. | Rewards joining Dependencies with Backlog.SprintID; a good plan must not violate ordering. | Join both dependency ends to Backlog.SprintID and check from-sprint >= to-sprint.
DUP-T-217 | Duplicate / Redundant ticket | Backlog!T-217 | Ticket T-217 'Add tests for schema registry' is a semantic duplicate of T-117 'Test schema registry'. | Semantic (not exact) match; rewards embedding/similarity or careful reading over string equality. | Compare ticket titles by meaning within the same Layer/SADSection.
PTS-ZERO-T-118 | Estimation / Unestimated work | Backlog!T-118 | Ticket T-118 'Automate stream consumer' has 0 story points. | Unestimated work breaks capacity forecasting; Scrum Master must force estimation. | Filter Backlog where Type in (Story,Task) and StoryPoints = 0.
PTS-ZERO-T-115 | Estimation / Unestimated work | Backlog!T-115 | Ticket T-115 'Provision OIDC client' has 0 story points. | Unestimated work breaks capacity forecasting; Scrum Master must force estimation. | Filter Backlog where Type in (Story,Task) and StoryPoints = 0.
PTS-ZERO-T-141 | Estimation / Unestimated work | Backlog!T-141 | Ticket T-141 'Document availability service' has 0 story points. | Unestimated work breaks capacity forecasting; Scrum Master must force estimation. | Filter Backlog where Type in (Story,Task) and StoryPoints = 0.
PTS-ZERO-T-139 | Estimation / Unestimated work | Backlog!T-139 | Ticket T-139 'Provision availability service' has 0 story points. | Unestimated work breaks capacity forecasting; Scrum Master must force estimation. | Filter Backlog where Type in (Story,Task) and StoryPoints = 0.
ORPHAN-T-214 | Orphan / Broken hierarchy | Backlog!T-214 | Ticket T-214 references ParentID 'F-99' which does not exist in Backlog. | Only visible when joining child->parent; breaks Epic->Feature->Story rollup. | Left-join Backlog.ParentID to Backlog.TicketID; nulls = orphans.
ORPHAN-T-215 | Orphan / Broken hierarchy | Backlog!T-215 | Ticket T-215 references ParentID 'EPIC-77' which does not exist in Backlog. | Only visible when joining child->parent; breaks Epic->Feature->Story rollup. | Left-join Backlog.ParentID to Backlog.TicketID; nulls = orphans.
ORPHAN-T-216 | Orphan / Broken hierarchy | Backlog!T-216 | Ticket T-216 references ParentID 'F-88' which does not exist in Backlog. | Only visible when joining child->parent; breaks Epic->Feature->Story rollup. | Left-join Backlog.ParentID to Backlog.TicketID; nulls = orphans.
DEP-ORPHAN-DEP-021 | Orphan dependency | Dependencies!DEP-021 | DEP-021: T-162 depends on 'T-9999' which is absent from Backlog. | Only found by joining Dependencies.ToTicketID to Backlog.TicketID; blocks planning silently. | Left-join Dependencies.ToTicketID (and FromTicketID) to Backlog.TicketID; nulls = orphan edges.
AC-MISS-T-150 | Readiness / Missing acceptance criteria | Backlog!T-150 | Ticket T-150 'Provision DMS connector' has no acceptance criteria and no DoD. | Definition of Ready is violated; ticket should not be sprint-committed until refined. | Filter Backlog.HasAcceptanceCriteria = 'N' (or HasDoD='N').
AC-MISS-T-138 | Readiness / Missing acceptance criteria | Backlog!T-138 | Ticket T-138 'Automate pricing rules' has no acceptance criteria and no DoD. | Definition of Ready is violated; ticket should not be sprint-committed until refined. | Filter Backlog.HasAcceptanceCriteria = 'N' (or HasDoD='N').
AC-MISS-T-145 | Readiness / Missing acceptance criteria | Backlog!T-145 | Ticket T-145 'Integrate workshop slot API' has no acceptance criteria and no DoD. | Definition of Ready is violated; ticket should not be sprint-committed until refined. | Filter Backlog.HasAcceptanceCriteria = 'N' (or HasDoD='N').
AC-MISS-T-195 | Readiness / Missing acceptance criteria | Backlog!T-195 | Ticket T-195 'Test contract test' has no acceptance criteria and no DoD. | Definition of Ready is violated; ticket should not be sprint-committed until refined. | Filter Backlog.HasAcceptanceCriteria = 'N' (or HasDoD='N').
AC-MISS-T-154 | Readiness / Missing acceptance criteria | Backlog!T-154 | Ticket T-154 'Design event publisher' has no acceptance criteria. | Definition of Ready is violated; ticket should not be sprint-committed until refined. | Filter Backlog.HasAcceptanceCriteria = 'N' (or HasDoD='N').
AC-MISS-T-104 | Readiness / Missing acceptance criteria | Backlog!T-104 | Ticket T-104 'Document transit gateway' has no acceptance criteria and no DoD. | Definition of Ready is violated; ticket should not be sprint-committed until refined. | Filter Backlog.HasAcceptanceCriteria = 'N' (or HasDoD='N').
SAD-UNTRACE-EPIC-14 | Traceability / Unanchored Epic | Backlog!EPIC-14 | EPIC-14 references SADSectionID 'SAD-99' which is absent from SAD_Sections. | Every Epic must roll up to a SAD section; unanchored scope signals gold-plating. | Left-join Backlog.SADSectionID to SAD_Sections.SectionID; nulls = untraceable.